## CONTACTS
[Your Event] Contacts
Section | Who | Name | What for | Phone | Email
Executive team |  | Event | Coordinator
Bar | Liquor Licence |  | Licencing
Bar | Bar suppliers |  | Supply beer at cost
Kids' Entertainment |  |  | Sponsorship
Kids' Entertainment | Face painter
Entertainer |  |  | Celebrity chef
Entertainer |  |  | Celebrity gardener
Marketing |  |  | Advertising
Marketing |  |  | Sponsorship
MC |  |  | Audio visual
Operations | Water truck |  | Stop dust on the road
Operations | Portable toilets |  | Portaloos
Operations | Event hire |  | Marquees
Operations | Sand supplier for kids sandpit |  | Sand
Operations | Road corridor permit |  | Traffic
Sustainability |  |  | Recycling
Volunteers |  |  | Printing of volunteer lanyards

## EVENT DELIVERY DAYS
This example is for a one day food festival. Delete the content and update the template for your event.
Responsible area | KEY TASK & MILESTONES | TIMELINE | ✔ | Is a runsheet required?
Bar | Be onsite to ensure marquee, ice trough and tables are set up on level ground. | Day before event
Bar | Be onsite for delivery of beer and wine and do a stock take to ensure it is all there. | Day before event
Bar | At the end of the day do a stocktake and make notes of this for the post-event report. Collate what is left over and determine what sold best, what didn't sell well and provide recommendations for next year's event. | Day of event
Bar | Set up the stall and decorate, ensuring that RSA and licensing sign is displayed according to guidelines. | Day of event
Barbecue | At the end of the day do a stocktake of what meat is left over and store it in the cold room. Make notes on this for the post-event report. Use leftovers for the volunteer thank you barbecue. | Day of event
Barbecue | Ensure volunteers are adhering to the food safety guidelines. | Day of event
Barbecue | Ensure food handling guidelines are on display, and that soap and hand towels are available. | Day of event
Barbecue | Manage the stall and volunteers. The coordinator should not commit to a role on the day e.g. cooking. | Day of event
Barbecue | Ensure that no food is consumed by volunteers near the barbecue area. Ensure they go to the staff area for meals. | Day of event
Children | Set up the kids activities. | Festival weekend
Children | Coordinate volunteers, answer questions and assist children. | Day of event
Executive Team | Coordinate and oversee the smooth flow of the dinner event. | Day before event |  | Yes - Refer Gala Dinner Run Sheet
Executive Team | Monitor flow of visitors through the site and queues and record suggested changes for next year. | Festival weekend
Executive Team | Surveys. | Day of event
Finance | Introduce the finance team to all the stall coordinators at the start of the day. | Day of event
Finance | Work with the Stallholder Coordinator to invoice and receive stallholder payments. Send receipts to the Stallholder Coordinator and follow up on late payments. | Ongoing
Main marquee | Hang sponsorship signs. | Day before event
Main marquee | Set up and decorate marquee. | Day before event
Marketing | Load survey forms to the website. | Festival Weekend
MC | Pre-check with sound people well before the 9am start on Sunday. | Day before event
MC | Set up all sound gear on Saturday. | Day before event
MC | Communicate regularly with stalls re:stock and make relevant announcements throughout the day. | Day of event
MC | Achieve balance between getting the announcements out and disturbing attendees with noise. | Day of event
MC | Do all the outside announcements from 9am to 4pm. | Day of event
MC | Ensure celebrities are at the correct locations at the correct times for outside events. | Day of event
Merchandise | Deliver selected merchandise at other strategic places around the festival site e.g. bar for stubby holders, insulated bags with stalls selling product to keep cold, as arranged with relevant coordinators. | Day before event
Merchandise | Stocktake at end of the day and make notes for post event report. | Day of event
Music | Set up signs and decorations. | Day before event
Music | Direct performers to the stage and ensure they have everything they need. | Day of event
Music | MC the music tent, ensuring a good flow of music throughout the day. | Day of event
Operations | Ensure Stallholder Coordinator has enough walkie talkies for all volunteers. | Day before event
Operations | Coordinate the set up and pull down of fencing and signs once the traffic management role has been completed. | Festival weekend
Operations | Coordinate the bump in of all infrastructure. | Festival weekend
Operations | Collect the lunch for the SES at the time agreed with Barbecue Coordinator. | Day of event
Operations | Coordinate communication between SES and MC during the day. Hold a debrief meeting with SES staff and volunteers once it is clear that the traffic management role has been completed. | Day of event
Stallholders | Mark out the site with site numbers. | Day before event
Stallholders | Liaise with electrician and ensure all power requirements are safe and working. | Festival weekend
Stallholders | Ensure stallholders are settled, setup and vehicles are off site by 8am. | Day of event
Stallholders | Mark off stallholders as they arrive. | Day of event
Stallholders | Set up and monitor the smooth flow of presenters into the marquee. Ensure it is kept clean and tidy between presentations and ensure speakers are briefed 15min before their talk. | Day of event
Stallholders | Monitor stallholders during the day. Check they are happy and are selling what was agreed to. Get feedback and note general feel. | Day of event
Stallholders | Check the list of goods intended to be sold by the stallholder listed on their application form. Refuse products if they don’t fit in with values of the event e.g. product not made by stallholder or multi components eg coffee, biscuits, preserves etc. | Ongoing
Volunteers | Reallocate volunteers to areas if necessary ensuring everyone has adequate support. | Festival weekend
Volunteers | Hand out lanyards to volunteers as they arrive. | Festival weekend
Volunteers | Coordinate floaters and roamers and be a support person during the day. | Day of event
Volunteers | Ensure stallholders/coordinators have enough helpers. | Day of event
Volunteers | Coordinate volunteer roster at information tent. | Day of event

## EXAMPLE_DINNER EVENT RUN SHEET
Gala Dinner - DATE - TIME - LOCATION
| Activity | Who | Requirements | Notes
Pre arrival
5pm (arrival) | Greet guests at the door |  |  | Ensure someone is ready to personally look after sponsors and VIPs.
5.30pm | Oyster Bar opens
6.00pm | MC asks all guests to be seated for the dinner | MC | Audio, table seating plan, ushers to move people from standing bar and Oyster area to seated area.
6.10pm | Welcome to / Acknowledgement of Country
6.20pm | Official welcome by Mayor
6.30pm | Entrée served with gentle background music
7.00pm | Main meal served and head chef to talk to about produce used | Chef, kitchen staff, MC
8.00pm | Dessert served
8.30pm | Live band to commence entertainment
10.00pm | Last drinks and event wrap up

## EXAMPLE_WORKSHOP RUN SHEET
Workshops Day 1 — Time, Date and Location
| Activity | Who | Requirements | Notes
Pre-arrival
9am
10am
11am
12pm
1pm
2pm
3pm
4pm