## Event Timeline
| Key Tasks & Milestone [Update the key tasks and milestones in the example below for your event] | Timeline | Post event | Event planning | Finance | Sponsorship | Grand funding | Risk management / Operations | Marketing plan | Working with media | Digital marketing | Volunteers | Logistics | Responsible executive area | ✔
Preplanning stage | Hold an Executive Committee strategy session (SWOT analysis, goals and vision, mission and values). | 10 months before event |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | Executive committee
Preplanning stage | Review and update strategic plan, timeline and committee structure, and determine changes/additions to be presented at public meeting. | 10 months before event |  | ✔ | [9 empty] | Executive committee
Preplanning stage | Update committee roles and responsibilities checklists in preparation for handover at the public meeting | 10 months before event |  | ✔ | [7 empty] | ✔ |  | Executive committee
Preplanning stage | Prepare packs for coordinators e.g. event planning timeline, event manual, strategic plan, previous event report and recommendations. | 10 months before event |  | ✔ | [7 empty] | ✔ |  | Executive committee
Preplanning stage | Review post-event report from the previous year to ensure the recommended enhancements and changes are taken into consideration. Review event trends and what other similar events are doing. | Ongoing | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | Executive committee
Preplanning stage | Develop event budget and have it endorsed by the Executive Committee. | 10 months before event |  | ✔ | ✔ | [8 empty] | Finance
Preplanning stage | Manage the event budget. Issue and pay invoices and keep the budget actuals up-to-date. | Ongoing |  |  | ✔ | [8 empty] | Finance
Preplanning stage | Undertake a review of the website and implement changes and additions for this year. | 10 months before event |  | ✔ |  |  |  |  | ✔ |  | ✔ |  |  | Marketing
Preplanning stage | Develop marketing plan and have it endorsed by the Executive Committee. | 10 months before event | [6 empty] | ✔ |  |  |  |  | Marketing
Preplanning stage | Coordinate meetings with major funding partners to establish funding for the year. | 10 months before event |  |  |  |  | ✔ |  | ✔ |  |  |  |  | Marketing
Preplanning stage | Send regular updates to sponsors, partners and stakeholders to keep them informed of the event's planning progress. | Ongoing |  |  |  | ✔ |  | ✔ | ✔ |  |  |  | ✔ | Marketing
Preplanning stage | Activate the marketing plan and acquire sponsorship. | Ongoing | [6 empty] | ✔ |  |  |  |  | Marketing
Preplanning stage | Develop and maintain an inventory of infrastructure needs and providers e.g. suppliers of tents, tables, chairs, cash drawers, etc. | Ongoing | [10 empty] | ✔ | Operations
Preplanning stage | Get quotes for infrastructure. Present to the Executive Committee and, once endorsed, place orders. | 10 months before event | [5 empty] | ✔ |  |  |  |  | ✔ | Operations
Preplanning stage | Maintain the volunteer roster; liaise with Subcommittee Coordinators to identify gaps. Regularly recruit new volunteers. | Ongoing |  | ✔ | [7 empty] | ✔ |  | Volunteers
Working stage | General meeting. Secure Sub-Committee Coordinators as per the committee structure. | 9 months before event |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | Executive committee
Working stage | Executive Committee meeting. | 9 months before event |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | Executive committee
Working stage | Develop the shell program and decide on feature elements, entertainment, etc. | 9 months before event |  | ✔ | [9 empty] | Executive committee
Working stage | Book musicians, presenters, etc. | 9 months before event |  | ✔ | [9 empty] | Executive committee
Working stage | Update website and social media with date and program information. | 9 months before event |  | ✔ |  |  |  |  | ✔ |  | ✔ |  |  | Marketing
Working stage | Develop sponsor prospectus and a targeted hit list, and start negotiations. | 9 months before event |  |  |  | ✔ |  |  | ✔ |  |  |  |  | Marketing
Working stage | Start working on Traffic Management Plan and Event Management Plan. | 9 months before event |  | ✔ |  |  |  | ✔ |  |  |  |  | ✔ | Operations
Working stage | Develop a Parking Plan. | 9 months before event |  | ✔ |  |  |  | ✔ |  |  |  |  | ✔ | Operations
Working stage | Executive Committee meeting. | 8 months before event |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | Executive committee
Working stage | Review the post-event report and action items that have been recommended for improvement .Provide to Sub-Committee Coordinators as required. | 8 months before event |  | ✔ | [8 empty] | ✔ | Executive committee
Working stage | Develop and distribute save the date collateral. | 8 months before event | [6 empty] | ✔ |  |  |  |  | Marketing
Working stage | Develop a Social Media Content Plan for commencement next month. | 8 months before event | [6 empty] | ✔ |  | ✔ |  |  | Marketing
Working stage | Start monthly email newsletter to database/subscribers. | 8 months before event | [6 empty] | ✔ |  |  |  |  | Marketing
Working stage | Continue sponsor negotiations with the aim of locking away major sponsors this month. | 8 months before event |  |  |  | ✔ | ✔ |  | ✔ |  |  |  |  | Marketing
Working stage | Develop accommodation packages. | 8 months before event | [6 empty] | ✔ |  |  |  |  | Marketing
Working stage | Book SES for traffic management. | 8 months before event |  | ✔ |  |  |  | ✔ |  |  |  |  | ✔ | Operations
Working stage | Develop Sign Plan. | 8 months before event |  | ✔ |  |  |  | ✔ |  |  |  |  | ✔ | Operations
Working stage | Book ambulance / first aid providers. | 8 months before event | [5 empty] | ✔ |  |  |  |  | ✔ | Operations
Working stage | Finalise quotes for infrastructure and book equipment. | 8 months before event | [5 empty] | ✔ |  |  |  |  | ✔ | Operations
Working stage | Executive Committee meeting. | 7 months before event |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | Executive committee
Working stage | Update Risk Management Plan. | 7 months before event |  | ✔ |  |  |  | ✔ |  |  |  |  | ✔ | Executive committee
Working stage | Finalise approvals, licenses, insurance e.g. liquor license, traffic management, development approval, insurance, road sign permits, food license, etc. | 7 months before event |  | ✔ |  |  |  | ✔ |  |  |  |  | ✔ | Executive committee
Working stage | Update third party online event listings with new details e.g. Australian Tourism Data Warehouse. | 7 months before event | [6 empty] | ✔ |  | ✔ |  |  | Marketing
Working stage | Update website with new content including sponsor details. | 7 months before event | [6 empty] | ✔ |  | ✔ |  |  | Marketing
Working stage | Source advertising quotes and media partners. | 7 months before event | [6 empty] | ✔ | ✔ |  |  |  | Marketing
Working stage | Finalise sponsorship negotiations and ensure agreements/contracts are signed. | 7 months before event |  |  |  | ✔ | ✔ |  | ✔ |  |  |  |  | Marketing
Working stage | Finalise travel packages and upload to website. | 7 months before event | [6 empty] | ✔ |  | ✔ |  |  | Marketing
Working stage | Finalise Traffic Management Plan and Event Management Plan, share with the committee and submit to TRC and local authorities. | 7 months before event |  | ✔ |  |  |  | ✔ |  |  |  |  | ✔ | Operations
Working stage | Executive Committee meeting. | 6 months before event |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | Executive committee
Working stage | Finalise merchandise and place any orders. | 6 months before event |  | ✔ |  |  |  |  | ✔ |  |  |  |  | Executive committee
Working stage | Finalise program shell ready to start approaching performers, presenters, etc. | 6 months before event |  | ✔ |  |  |  |  | ✔ |  |  |  |  | Executive committee
Working stage | Contact Sub-Committee Coordinators and ask them to provide information for the website. | 6 months before event |  | ✔ |  |  |  |  | ✔ |  |  | ✔ | ✔ | Marketing
Working stage | Load expressions of interest documents for performers, stallholders, volunteers to the website and put out a call on social media. | 6 months before event | [6 empty] | ✔ |  | ✔ |  |  | Marketing
Working stage | Source advertising quotes and media partner proposals. | 6 months before event | [6 empty] | ✔ | ✔ |  |  |  | Marketing
Working stage | Publicise local accommodation options to potential attendees. | 6 months before event | [6 empty] | ✔ |  |  |  |  | Marketing
Working stage | Get information on equipment from Sub-Committee Coordinators. | 6 months before event |  | ✔ | [8 empty] | ✔ | Operations
Working stage | Finalise equipment requirements and place orders. | 6 months before event |  | ✔ | [8 empty] | ✔ | Operations
Working stage | Finalise the Sign Plan and determine additional sign requirements. Order signs. | 6 months before event |  | ✔ | [8 empty] | ✔ | Operations
Working stage | Executive Committee and Sub-Committee Coordinators meeting. | 5 months before event |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | Executive committee
Working stage | Develop detailed program and schedules for event day. Seek feedback from Sub-Committee Coordinators, update, and then provide to he Marketing Coordinator. | 5 months before event |  | ✔ | [8 empty] | ✔ | Executive committee
Working stage | Lock in advertising. | 5 months before event | [6 empty] | ✔ | ✔ | ✔ |  |  | Marketing
Working stage | Sub-Committee Coordinators notify Volunteer Coordinator of their volunteer needs, and Finance Coordinator of their float requirements. | 5 months before event | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | Finance
Working stage | Recruit volunteers. | 5 months before event | [9 empty] | ✔ |  | Volunteers
Working stage | Design, print and distribute marketing collateral. | 4 months before event | [6 empty] | ✔ |  |  |  |  | Marketing
Working stage | Update website including program, entertainment schedule and profiles, accommodation packages, sponsor details, etc. | 4 months before event | [6 empty] | ✔ |  | ✔ |  |  | Marketing
Working stage | Liaise with TRC regarding site preparation support. | 4 months before event |  | ✔ | [8 empty] | ✔ | Operations
Working stage | Commence site preparation. | 4 months before event | [10 empty] | ✔ | Operations
Working stage | Executive Committee meeting. | 3 months before event |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | Executive committee
Working stage | Finalise the Site Plan, share with coordinators, and load to the website. | 3 months before event |  | ✔ |  |  |  |  | ✔ |  |  |  | ✔ | Executive committee
Working stage | Order food and supplies. | 3 months before event |  | ✔ | [8 empty] | ✔ | Executive committee
Working stage | Finalise program and provide to the Marketing Coordinator. | 3 months before event |  | ✔ |  |  |  |  | ✔ |  |  |  |  | Executive committee
Working stage | Commence advertising and promotion in earnest. | 3 months before event | [6 empty] | ✔ | ✔ | ✔ |  |  | Marketing
Working stage | Make arrangements for recycling and waste management. | 3 months before event |  | ✔ | [8 empty] | ✔ | Operations
Working stage | Confirm performers, infrastructure, licensing, etc. Establish a folder with everything required on the day including contacts and documents. | 2 months before event | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | Executive committee
Working stage | Executive Committee and Sub-Committee Coordinators meeting. | 2 months before event |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | Executive committee
Working stage | Brief performers. | 2 months before event |  | ✔ | [8 empty] | ✔ | Executive committee
Working stage | Invite key stakeholders. | 2 months before event |  | ✔ |  | ✔ | ✔ | [6 empty] | Executive committee
Working stage | Finalise site preparation and shareSsite Plan with stakeholders and volunteers. | 2 months before event |  | ✔ | [8 empty] | ✔ | Operations
Working stage | Hold an onsite meeting with electrician, AV supplier and other key suppliers. | 2 months before event |  | ✔ |  |  |  | ✔ |  |  |  |  | ✔ | Operations
Working stage | Continue to source volunteers and draft rosters. | 2 months before event | [9 empty] | ✔ |  | Volunteers
Working stage | Ensure volunteer forms are returned by the middle of the month and finalise volunteer roster. | 2 months before event | [9 empty] | ✔ |  | Volunteers
Working stage | Plan volunteer thank you function and send invitations. | 2 months before event | [9 empty] | ✔ |  | Volunteers
Event delivery | Hold a coordinators briefing so all coordinators understand the complexity of other coordinators' roles and risk management. | 1 month before event | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | Executive committee
Event delivery | Executive Committee and Sub-Committee Coordinators meeting. | 1 month before event |  | ✔ | ✔ | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | Executive committee
Event delivery | Finalise logistics including run sheets, rosters, MC notes, checklists, etc. | 1 month before event |  | ✔ | ✔ | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | Executive committee
Event delivery | FInalise programs. | 1 month before event |  | ✔ |  |  |  |  | ✔ |  |  |  | ✔ | Executive committee
Event delivery | Create surveys for post-event distribution. | 1 month before event | ✔ | ✔ |  |  |  |  | ✔ |  |  |  |  | Executive committee
Event delivery | Commence short lead advertising. | 1 month before event | [6 empty] | ✔ | ✔ |  |  |  | Marketing
Event delivery | Plan the communication method during the event e.g. phones and/or two way radios. | 1 month before event |  | ✔ | [8 empty] | ✔ | Operations
Event delivery | Finalise volunteer rosters and send to each volunteer with induction pack. | 2 weeks before event | [9 empty] | ✔ |  | Volunteers
Event delivery | Establish cash floats. | 1 week before event |  |  | ✔ | [8 empty] | Finance
Event delivery | Oversee large infrastructure assembly e.g marquees. | 1 week before event | [10 empty] | ✔ | Operations
Event delivery | Monitor flow of visitors through site, queues etc. to inform planning for next year. | Event day | ✔ | ✔ | [8 empty] | ✔ | Executive committee
Event delivery | Coordinate the set up and pull down of fencing and signs. | Event day |  | ✔ |  |  |  | ✔ |  |  |  |  | ✔ | Operations
Event delivery | Coordinate the bump in of infrastructure. | Event day |  | ✔ | [8 empty] | ✔ | Operations
Event delivery | Sound check before event. | Event day |  | ✔ | [8 empty] | ✔ | Operations
Event delivery | If necessary reallocate volunteers to ensure adequate support. | Event day | [9 empty] | ✔ |  | Volunteers
Event delivery | Distribute links to surveys at the end of the event. | Event day | [9 empty] | ✔ |  | Executive committee
Post-event/Preplanning | Provide formal thank yous to volunteers and key stakeholders, and encourage their feedback. | First week after event | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | Executive committee
Post-event/Preplanning | Coordinate thank you function and debrief. | First week after event | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | Executive committee
Post-event/Preplanning | Select date for the next event, book the site/venue, and share the date on social media and website. | First week after event | ✔ | ✔ | [9 empty] | Executive committee
Post-event/Preplanning | Add a photo gallery to the website and provide link to Event Coordinator for social media. | First week after event | ✔ | [5 empty] | ✔ |  | ✔ |  |  | Marketing
Post-event/Preplanning | Develop and distribute post-event wrap-up media release. Reuse as a blog article, and share in newsletter and on social media, etc. | First week after event | ✔ | ✔ |  |  |  |  | ✔ | ✔ |  |  |  | Marketing
Post-event/Preplanning | Have Sub-Committee Coordinators review their planning timelines and make adjustments for next year. | First week after event | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | Executive committee
Post-event/Preplanning | Take down, clean, audit and store signs, and update the asset register. | First week after event | ✔ | [9 empty] | ✔ | Operations
Post-event/Preplanning | Hold a meeting with SES to discuss feedback on the traffic management and recommendations for next year. | First week after event | ✔ |  |  |  |  | ✔ | [5 empty] | Operations
Post-event/Preplanning | Prepare and finalise finances and develop and present a final financial report to the Executive Committee. | Second week after event | ✔ | ✔ | ✔ | [8 empty] | Finance
Post-event/Preplanning | Acquit grants and sponsorship agreements. | Second week after event | ✔ |  |  | ✔ |  |  | ✔ |  |  |  |  | Marketing
Post-event/Preplanning | Collate feedback from surveys. | Second week after event | ✔ | ✔ |  |  |  |  | ✔ |  |  |  |  | Executive committee
Post-event/Preplanning | Develop Google Analytics reports for the Post-Event Report. | Second week after event | ✔ | [5 empty] | ✔ |  | ✔ |  |  | Marketing
Post-event/Preplanning | Develop event report and provide to Executive Committee and stakeholders. | Second week after event | ✔ | ✔ | ✔ | ✔ |  | ✔ | ✔ | ✔ | ✔ | ✔ | ✔ | Executive committee
Post-event/Preplanning | Update website . | Second week after event | ✔ | [5 empty] | ✔ |  | ✔ |  |  | Marketing