## Phases
Phase | Activities | Channels Used | Suggested Messages
1. Pre-event awareness 10–6 months prior | Quickly building targeted reach and awareness. | Organic social media | Save the date in your calendar
| Artist and stallholder applications. | Website
| Event information. | Direct marketing (email and phone)
Content creation
2. Pre-event consideration 5–3 months prior | Targeted activity to an engaged audience. | Digital advertising | How to get involved in this year’s event (sponsor, volunteer, stallholder, entertainment, etc.).
| Sell tickets. | Social media advertising
| Event information. | Direct marketing | Promote key program elements.
Influencer campaign
3. Pre-event conversion From three months prior | Tickets on sale and last chance messaging. | Digital advertising | Tickets on sale.
Book accommodation (link to options).
| News. | Social media advertising | Itineraries (make a weekend of it).
|  | Direct marketing | Event countdown. Top 10 great things about the event (or top 10 great things for e.g. families, campers, etc.).
| Sell tickets. | PR and Media
| Drive FOMO (fear of missing out). | Traditional marketing (TV, print, radio) | Newsworthy item relevant to your event.
Plan your weekend — itineraries, attractions, things to do, etc.
Preparing for the event — weather, what to bring, maps/directions, program download, etc.
4. Event During event | Up-to-date info. | Organic social media | User generated content.
| User-generated content. |  | Live Facebook videos.
5. Post-event Week after | Festival wrap. | Organic social media | How it went (numbers of attendees/stallholders, images gallery, testimonial, etc.)
| Highlights. |  | Thank you to sponsors and volunteers.
| Date for next year. |  | Provide your feedback (link to survey).

## Marketing Schedule
© Copyright rEVENTS Academy - Not for sale or distribution. All rights reserved.
Budget | Weeks to eevnt | -16 | -15 | -14 | -13 | -12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 0 | 1 | 2 | 3
Week commencing (Sunday)
N/A | Key event dates
100 day event launch (save the date)
10 week countdown
Event registration open
Tickets on sale
Visitor survey
Event Website | Event Website
100 day event launch — site ready
Event registration open
Tickets on sale
Visitor survey link live
Official event photos live
Crosslink social media with website
Digital advertising | Digital advertising
Organic social
Facebook
Instagram
Twitter/YouTube/Other
Online sdvertising
Keyword research and SEO review
Social advertising campaigns
Website/Social takeovers
Editorial coverage
Banner advertising
Email newsletter
Sponsorship proposals
Save the date
Event registration opens
General Event Promotion
Tickets on sale
Event evaluation survey
Newspaper advertising | Newspaper advertising
Inserts
Program
Page ads
Whats on at event ad
Editorial coverage
Media releases
Outdoor advertising | Outdoor advertising
Distribution of event flyers
100 day launch
Street banners
Roadside signs
Product placement (flyers, bus wraps, etc.)
Radio/TV | Radio/TV
Event promotion
PR | PR
100 day launch
Famil/hosting influencers/bloggers/ambassadors
Media interviews
Retail & hospitality activation | Retail & hospitality activation
| Sponsorship engagement | Prior to
Themed shop window displays

## Awareness Content Calendar
Activity | Week | Week | Week | Week | Week | Week
Key messages
Important dates
Website/Blog
Website
1–2 blogs per month
EDM
Media release
Facebook
Paid
Organic (five/week)
Monday
Tuesday
Thursday
Sunday
Instagram (four/week)
1
2
3
4
Other
Other

## Consideration Content Calendar
Activity | Week | Week | Week | Week | Week | Week
Key messages
Important dates
Website/Blog
Website
1–2 blogs per month
EDM
Media release
Facebook
Paid
Organic (five/week)
Monday
Tuesday
Thursday
Sunday
Instagram (four/week)
1
2
3
4
Other
Other

## Conversion Content Calendar
Activity | week | week | week | week | week | week
Key messages
Important dates
Website/Blog
Website
1–2 blogs per month
EDM
Media release
Facebook
Paid
Organic (five/week)
Monday
Tuesday
Thursday
Sunday
Instagram (four/week)
1
2
3
4
Other
Other

## During Content Calendar
Activity | week | week | week | week | week | week
Key messages
Important dates
Website/Blog
Website
1–2 blogs per month
EDM
Media release
Facebook
Paid
Organic (five/week)
Monday
Tuesday
Thursday
Sunday
Instagram (four/week)
1
2
3
4
Other
Other

## Post Content Calendar
Activity | week | week | week | week | week | week
Key messages
Important dates
Website/Blog
Website
1–2 blogs per month
EDM
Media release
Facebook
Paid
Organic (five/week)
Monday
Tuesday
Thursday
Sunday
Instagram (four/week)
1
2
3
4
Other
Other